## Slide 1
EG334S · INDIVIDUAL PRESENTATION
Delivering a Multi-Cloud Build
Programme management, security posture and cost control
across AWS and Azure
Bernard Tay
Technical Programme Manager · Security & Monitoring
HyEnt · 3 cloud cells · 2 VPN connections · 2 providers
Notes: Open with the result: three cloud cells, two providers and two VPN connections. My role was delivery, security/monitoring and cost control. Keep to 30 seconds.
[Sources]
- Project Information.pdf (provided module brief)
- https://docs.aws.amazon.com/vpn/latest/s2svpn/

## Slide 2
WHAT I WILL COVER
Agenda
1
The system we built
Three cells, two VPN connections, 60 seconds of context
2
How I planned it
Back-planned from the deadline, not forward from day one
3
Security posture
What I locked down, and one constraint that reshaped the build
4
Cost control
The guardrails I put in, and why the daily one matters most
5
Constraints & workarounds
What went wrong and what I did about it
6
Results and what I learned
Evidence, and the finding I did not expect
My slice
Delivery & critical path
Risk register
Security group / NSG scoping
Cost guardrails
Teardown coordination
Notes: Signpost the sequence. Spend most time on my owned sections: delivery, security/monitoring and cost control.
[Sources]
- Presentation Assessment Rubrics.pdf (provided marking rubric)
- Project Information.pdf (provided module brief)

## Slide 3
SECTION 1, CONTEXT
Three cells, two VPN connections
Simulated on-prem
AWS us-east-1 · N. Virginia
10.0.0.0/16
strongSwan customer gateway
+ test server
AWS public cloud
AWS eu-west-1 · Ireland
10.1.0.0/16
Apache web server
THE HUB, both tunnels land here
Azure
southeastasia · Singapore
10.2.0.0/16
nginx web server
VPN #1
~69 ms
VPN #2
~189 ms
Two IPsec VPN connections cross the public internet. Latency reflects distance and routing.
TTL 254 is consistent with a routed hop. The stronger proof combines private addressing, provider telemetry, IPsec state and HTTP traffic.
Notes: Trace left to right. AWS public is the hub; two VPN connections terminate on one VGW. Each AWS connection has two tunnel endpoints. TTL is supporting evidence only; combine it with private addressing, telemetry, IPsec state and HTTP.
[Sources]
- https://docs.aws.amazon.com/vpn/latest/s2svpn/
- https://www.rfc-editor.org/rfc/rfc4301

## Slide 4
SECTION 2, DELIVERY
I planned backwards from the deadline
The fixed point
30 Aug 2026, 23:59
Formal mark penalty: AWS resources left running after this deadline. Our wider teardown covers AWS, Azure and monitoring.
The chain that decides the finish date
CIDR → networks → compute → VPN #1 → VPN #2 → test → demo → decommission
Anything off this chain is parallel work. If time runs short you protect the chain and sacrifice the rest, never the reverse.
Why the addressing scheme came first
Address overlap is a common cause of "VPN up, no traffic". Every later decision inherits from the addressing table, so we locked three non-overlapping ranges before build work began.
10.0.0.0/16
on-prem
10.1.0.0/16
AWS public
10.2.0.0/16
Azure
Notes: Say why backward planning mattered: the formal AWS teardown deadline cannot move. Locking CIDRs early protected every downstream route and tunnel configuration.
[Sources]
- Project Information.pdf (provided module brief)
- Amazon Virtual Private Cloud User Guide.pdf (provided course reference)

## Slide 5
SECTION 2, DELIVERY
Where we ended up
1
CIDR scheme locked
Three non-overlapping ranges
DONE
2
All three networks live
2 AWS VPCs + Azure VNet
DONE
3
First VPN passing traffic
on-prem ↔ AWS, 0% loss
DONE
4
Multi-cloud proven
ICMP + HTTP across providers
DONE
5
Assessed demonstration
this session
NEXT
6
Fully decommissioned
by 30 Aug 23:59
NEXT
Four of six milestones achieved, and we hit them roughly two weeks ahead of the planned dates.
The time we bought went into testing properly, capturing evidence while the system was live, and adding the monitoring layer.
Notes: Four milestones are achieved. The assessed demo and full teardown remain scheduled. Monitoring was prioritised over untested bonus features.
[Sources]
- Project Information.pdf (provided module brief)
- Presentation Assessment Rubrics.pdf (provided marking rubric)

## Slide 6
SECTION 3, MY SLICE
Security and monitoring posture
1
Scoped, not open
The AWS web server accepts ICMP and HTTP only from 10.0.0.0/16 and 10.2.0.0/16, the two networks that should ever reach it. Not 0.0.0.0/0.
2
Least privilege on the tunnel
IKE and NAT-T are the only inbound UDP ports on the gateway. Pre-shared keys are generated by the provider, never chosen by us and never committed to the repo.
3
A platform rule I designed around
Azure does not support attaching a network security group to the GatewaySubnet. Doing so can stop the gateway working. The NSG binds to the workload subnet only. Deliberate, not an omission.
4
Detection, not just prevention
CloudTrail management events with log validation, VPC Flow Logs metadata from both VPCs, and metric-math VPN alarms feeding SNS.
Known gap, stated up front and then closed: SSH was initially open to 0.0.0.0/0 on the lab hosts. Since the 25 Jul rebuild it is restricted to a single administrative /32, and the hub has no SSH ingress rule at all.
Notes: Four controls: scoped ingress, limited VPN ports/secret handling, Azure GatewaySubnet constraint, and detective monitoring. SSH is now restricted; do not say it remains open. Current VPN2 alarm may be expected while Azure is parked.
[Sources]
- https://docs.aws.amazon.com/vpc/latest/userguide/security-groups.html
- https://docs.aws.amazon.com/vpc/latest/userguide/flow-logs.html
- https://docs.aws.amazon.com/awscloudtrail/latest/userguide/cloudtrail-concepts.html
- https://learn.microsoft.com/azure/vpn-gateway/vpn-gateway-about-vpngateways

## Slide 7
SECTION 4, MY SLICE
Cost control was a delivery risk, not a finance one
The brief penalises AWS resources left running after the deadline. I used cost monitoring to detect forgotten resources, not just spending.
What was already there
A $296.90 account budget
Useless as a tripwire. At a measured $11.50/day it would take months to trip, long past the deadline that actually costs marks.
What I added
A $3/day tripwire
Sized to the actual risk. If anything is still running the morning after a work session, I know within a day.
$40
Monthly budget
alerts at 50 / 80 / 100% + forecast
$3
Daily tripwire
catches "left running" within a day
$25
Azure budget
added after finding Azure had none at all
09:00
Daily resource check
lists running EC2, VPNs, EIPs in both regions
The insight: a control only protects you if it is sized to the real risk, pointed at the right system, and re-aimed when that system is replaced.
The budget was too high to fire in time, and guardrails were initially on AWS while Azure carried most out-of-pocket cost.
Notes: Separate the cost views: about $11.50/day observed resource usage fully built; about $7.85/day Azure; AWS net about $0 after credits; parked Azure estimate about $0.44/day. The lesson is to put controls where out-of-pocket risk exists and re-aim them after rebuilds.
[Sources]
- Project report, Section 5.7 (team evidence)
- AWS Cost Explorer and Azure Cost Management observations captured for the project

## Slide 8
SECTION 5, CONSTRAINTS & WORKAROUNDS
Constraints, and what I did about them
AWS gives you only half a VPN
It supplies the Virtual Private Gateway and expects you to supply a real IPSec device at the other end. Our "on-prem" is a VPC. It has no such device.
WORKAROUND
Built one: an EC2 instance running strongSwan with an Elastic IP, registered as the Customer Gateway.
The account blocked me from deleting anything
A guardrail policy denied the automation IAM and delete actions. A failed stack then wedged, because rollback deletes resources and deletion was denied.
WORKAROUND
Deployed everything with --on-failure DO_NOTHING so a failure leaves a clean stack, and split VPN #2 into its own stack to limit blast radius.
Azure refused three VM sizes in a row
Availability and quota are two separate gates. The subscription had zero cores granted for the family we wanted.
WORKAROUND
Stopped guessing and read the quota directly. One command showed which family had headroom; that size deployed first time.
Eleven problems are documented in section 6 of the report. These three changed how I worked.
Notes: Take each constraint as problem then workaround. The report now records eleven problems. Emphasise learning applied forward, not the number alone.
[Sources]
- Project report, Section 6 (team evidence)
- https://docs.aws.amazon.com/AWSCloudFormation/latest/UserGuide/
- https://learn.microsoft.com/azure/quotas/

## Slide 9
SECTION 6, THE FINDING I DID NOT EXPECT
Both tunnels work.
On-prem still cannot reach Azure.
2 packets transmitted, 0 received, 100% packet loss
This is correct behaviour, not a fault.
An AWS Virtual Private Gateway does not provide transitive routing between VPN connections. Traffic arriving on one connection is not forwarded out of the other. The topology is hub-and-spoke: each spoke reaches the hub.
Why this matters
I tested it deliberately. Knowing the boundary of your own architecture is part of understanding it.
If it were required
Replace the Virtual Private Gateway with an AWS Transit Gateway, which does support transitive routing, but at higher hourly and per-attachment cost. The brief does not require it.
Notes: Set up the apparent contradiction, then explain it: two VPN connections can reach the hub, but the VGW does not forward traffic between them. Transit Gateway is the alternative if transitive routing becomes a requirement.
[Sources]
- Project report, Sections 6.9 and 7.7 (team evidence)
- https://docs.aws.amazon.com/vpc/latest/tgw/

## Slide 10
SECTION 6, RESULTS
How I know it works
I tested the control and data planes for each VPN, because an endpoint can report UP while carrying no traffic.
0%
packet loss, both VPN paths
254
consistent with a routed hop
6/6
tests with expected result
2
providers, one HTTP request
The strongest single result
curl http://10.1.1.x → <h1>EG334S · AWS public cloud</h1> (served by the template itself)
A complete application request, issued from a virtual machine in Azure in Singapore, crossed an encrypted tunnel over the public internet, was served by Apache in AWS in Ireland, and returned by the same path.
Control plane
Provider telemetry confirms an active endpoint for each VPN
Data plane
ICMP: 0% loss; TTL 254 supports the routed-path evidence
Application layer
HTTP served across two cloud providers
Negative test
Transitive path fails, as designed and documented
Notes: Lead with method: control plane plus data plane. Slow down for the Azure-to-AWS HTTP result. TTL supports the routed-path story but does not prove VPN traversal alone. The negative test documents the design boundary.
[Sources]
- Project report, Section 7 (team test evidence)
- https://www.rfc-editor.org/rfc/rfc4301

## Slide 11
SECTION 6, LESSONS
What I would tell myself at the start
1
“Tunnel UP” means almost nothing
It proves only that gateways negotiated. In this build, the data-plane faults were routing, source/destination checking or security groups. Test what you built before changing managed VPN settings.
2
Read the quota before choosing
I failed three deployments guessing at VM sizes. One command showed me exactly what the subscription was allowed to run. Diagnose, don't guess.
3
Permissions shape architecture
My first design used an IAM role the account forbade. The "best" design is worthless if the account won't let you build it. Check what you're allowed to do before designing around it.
4
Size the control to the risk
A budget far above lab-scale spending is a control that can never fire. Thresholds have to match the failure you are actually guarding against.
Notes: Lesson one is now evidence-based: our data-plane faults were routing, source/destination checking and security groups. Own the failed quota guesses and explain the improved method.
[Sources]
- Project report, Sections 6 and 8 (team evidence)

## Slide 12
PREPARED ANSWERS
Questions I expect
Q
Why is Azure in Singapore and not beside AWS in Ireland?
Deliberate trade-off. Ireland would give a ~15 ms tunnel, but every action in this demo would cross to Europe. Singapore gives a responsive demo at the cost of a longer tunnel, and tunnel latency is invisible to you, demo lag is not.
Q
Can the on-premises server reach Azure?
No, and that is by design. An AWS VGW does not do transitive routing. A Transit Gateway would enable it, at higher cost. The brief does not require it.
Q
Why two tunnels per VPN connection, with one down?
AWS always provisions two for redundancy. We configured one as active and one as standby. Both could be brought up for high availability.
Q
Did you implement CloudWatch, CloudTrail or Flow Logs?
Yes: multi-region CloudTrail with log validation; Flow Logs metadata from both VPCs to S3; and metric-math TunnelState alarms through SNS. MAX across each connection's two endpoints alarms only when neither is up. A parked VPN may intentionally alarm.
Q
What does this cost, and how do you control it?
Observed full-build usage was about $11.50/day. Azure contributed about $7.85/day, including about $5.04/day for its gateway; AWS net cost was about $0 after credits. The parked Azure estimate is about $0.44/day. Controls: AWS $40 monthly / $3 daily; Azure $25 monthly.
Q
How do you know nothing gets left running?
Three commands remove the core stacks/resource group. Then verify and remove out-of-stack alarms, dashboard, Flow Logs, CloudTrail/S3, SNS, budgets, Elastic IPs and tagged Azure resources.
Notes: Backup Q&A slide; do not present unless asked. For monitoring, distinguish management events and flow metadata. For cost, say “after credits.” For teardown, include out-of-stack controls. If live state is stale, say so.
[Sources]
- Project report, Sections 5.7, 7 and 8.3
- Project Information.pdf (provided module brief)
- https://docs.aws.amazon.com/vpn/latest/s2svpn/VPNTunnels.html

## Slide 13
IN SUMMARY
The system works, and
it will come down on time.
1
Three cloud cells, two providers, two IPsec VPN connections, verified at network and application layers.
2
Delivered roughly two weeks ahead of plan by back-planning from the deadline and protecting the critical path.
3
Cost controls detect chargeable resources before the 30 August AWS teardown deadline.
Thank you, happy to take questions, or demonstrate any part of it live.
Notes: Close on three points: verified system, early delivery and controlled teardown. Offer a live demonstration only after confirming the dashboard timestamp is current.
[Sources]
- Project report, Sections 7 and 8
- Project Information.pdf (provided module brief)